## Slide 1
HEC-RAS ETL
AUTOMATION PROGRAM
Project management roadmap for DYNAMO orchestration, Windows execution, and SVO-based ETL
Planning baseline
October 2026 – January 2028
DYNAMO + TWDB co-design
Notes: Melissa’s Team Feb and April are the Big times
Chris’s team are intermittent.
11 People
They will get me Rubrics for validating models and 2 models with outputs.
Pdf and Video Make it shorter
3pm friday

## Slide 2
HEC-RAS ETL AUTOMATION PROGRAM
Program objective and management logic
Build useful capability in vertical slices while the reusable ETL system matures.
Outcome 1
Run real HEC-RAS and HEC-HMS projects through a controlled Windows execution pool.
Outcome 2
Convert native model outputs into registered, visualizations and reporting.
Outcome 3
Give TWDB reviewers a repeatable notebook and reporting workflow with visible QA/QC.
Management rule
Every phase ends with a usable capability, a reviewable artifact, and a go/no-go decision for the next layer.
Project management view
02

## Slide 3
HEC-RAS ETL AUTOMATION PROGRAM
Target operating model
DYNAMO registers the HEC-RAS app, ETL transforms, and visualization scripts; the model bridge maps them into a dataset for review.
DYNAMO ARCHITECTURE + REGISTRIES
DYNAMO
Platform + API
Problem formulation
DYNAMO Model Bridge
Maps deconstructed execution,
ETL, and visualization pieces
DYNAMO registries
HEC-RAS Run
Orchestrator
Registered app
ETL
Registered transform
Visualization
Registered view
HEC-RAS EXECUTION
Windows worker pool
Pull + stage
Heartbeat + logs
HEC-RAS run
RasCommander
Versioned plan
Run files
HDF / geometry
Logs + metrics
DATASET + REVIEW
Registered ETL
Python transform
Write dataset
Dataset output
Canonical variables
Geometry + metadata
TWDB / Jupyter
Dataset review
Maps + metrics
dispatch
The dataset is the primary output; registered visualization scripts derive reviewer views from it.
Target operating model
03

## Slide 4
HEC-RAS ETL AUTOMATION PROGRAM
Workstreams and ownership
Three workstreams move in parallel, with co-design, bridge validation, and reporting development driving the delivery plan.
Build HEC-RAS pipeline
Co-design model set, reviewer sessions, acceptance criteria
Project lead + TWDB
Test DYNAMO Model Bridges
Validate registered bridges across execution, ETL, visualization, and dataset outputs
DYNAMO architecture team
Build Intelligent Reporting
Python visualization scripts, dataset views, reviewer reports
Python reporting team
Cross-cutting controls
Security and service accounts · versioned run manifests · reproducible environments · operator runbooks
Project management view
04

## Slide 5
HEC-RAS ETL AUTOMATION PROGRAM
Gantt schedule: build, deconstruction, reporting, and testing
The single-run slice establishes the evidence base; DYNAMO Model Bridge testing starts in January, and final setup begins in June.
WORKSTREAM
SCHEDULE
Oct
2026
Nov
Dec
Jan
Feb
Mar
Apr
May
Jun
Jul
2027
Environment baseline
Access, VMs, versions, sample models
Oct
Single-run slice
One model, one VM, one declared output
Nov–Dec
Test DYNAMO Model Bridges
Registered bridge testing across execution, ETL, visualization, and dataset outputs
Jan–May
Reviewer workflows
Notebook patterns, maps, metrics, feedback
Jan–May
Automated reporting
Reporting workflow developed Nov–May
Nov–May
Final setup
Integrated path, handoff, and final validation
Jun onward
builds on
Decision point
By July 2027, the integrated path should run a representative model, produce a declared output, generate a report, and pass TWDB review.
Gantt schedule
05

## Slide 6
HEC-RAS ETL AUTOMATION PROGRAM
Dependencies, risks, and decisions
The program can start while several decisions remain open, but they need owners and dates.
Dependency
Risk
Decision needed
Representative TWDB models
Toy examples hide version and file-layout problems
Select 5–10 models across 1D, 2D, RAS, and HMS
Unattended authentication
Duo or service-account policy can block automation
Approve the worker identity and token flow
Runtime and storage
Long jobs and large HDF outputs exceed defaults
Set wall-time, disk, archive, and retention policy
Output contracts
Ambiguous files create unsafe ETL inputs
Require declared output keys and checksums
Worker operations
A lost VM can strand a lease or duplicate a run
Define heartbeat, expiry, retry, and operator recovery
Program controls
09

## Slide 7
First 90 days
A clear first milestone makes the larger automation program manageable.
Weeks 1–4
Environment baseline
Confirm VM access, software versions, storage, authentication, and representative models.
Weeks 5–8
Single-run automation
Stabilize one representative model through staging, execution, status, output collection, and a notebook review.
Weeks 9–12
ETL proof + dataset contract
Produce one declared dataset output, review its QA/QC, and show one initial map or metric with TWDB.

## Slide 8
Kickoff questions
Confirm the conditions for the first representative ETL pipeline.
01 DOCUMENTATION ACCESS
Shared source materials
Where should the team find the current video, PDF, and workflow documentation, and which version is authoritative?
02 WORKING CADENCE
First ETL pipeline
Who needs to attend the working sessions, how often should they meet, and what decision must each session produce?
03 VISIBLE REVIEW OUTPUTS
First review artifact
What should the first notebook, map, metric, or report demonstrate to a TWDB reviewer?
04 MODEL ARCHIVES
Representative test set
Which 3–5 representative HEC-RAS model archives can TWDB share for testing across relevant model and software versions? For each, can you provide expected outputs and known limitations?